## Phase 1
| Relevant Section or Tool | FTEs (# on annual basis)* | Annual Cost/FTE** | Total Personnel | Other Program Expenses | Total Projected Expenses | Potential Revenue Sources
PHASE 1
1. Program Development
1.a. Assess Watershed & Community | 1.6 | 0.15 | 70000 | 10500 | 10000 | 20500 | General Fund, Grants
1.b. Conduct Program Self-Audit | 1.7, Tool #1 | 0.15 | 85000 | 12750 | 5000 | 17750
1.c. Develop Program Goals, Plan & Budget | 1.8 | 0.25 | 100000 | 25000 | 2000 | 27000
1.d. Develop & Implement Public Involvement Strategy | each chapter | 0.25 | 70000 | 17500 | 3000 | 20500
1.e. Hire Core Program Staff | Ch. 1 | 0.15 | 100000 | 15000 | 15000 | 30000
Task 1 Subtotal |  |  |  | 80750 | 35000 | 115750
2. Link Stormwater to Land Use
2.a. Establish Links to Planning Department | 2.5 | 0.1 | 100000 | 10000 |  | 10000 | General Fund
2.b. Evaluate Existing Land Use Codes | 2.6, Tool #3 | 0.15 | 70000 | 10500 | 2000 | 12500
2.c. Assess Integrated Stormwater/Land Use Tools | 2.7 | 0.2 | 70000 | 14000 | 1000 | 15000
2.d. Adopt Smart Growth Policies | Ch. 2, EPA docs | 0.2 | 85000 | 17000 | 2000 | 19000
Task 2 Subtotal |  |  |  | 51500 | 5000 | 56500
3. Adopt or Amend Stormwater Ordinance
3.a. Scope Out Ordinance Task | 3.2 | 0.02 | 100000 | 2000 |  | 2000 | General Fund
3.b. Identify MS4 Permit Requirements & Commitments | 3.2 | 0.02 | 85000 | 1700 |  | 1700
3.c. Identify State, Regional, or National Model Ordinance | 3.2, Tool #2 | 0.02 | 70000 | 1400 | 2000 | 3400
3.d. Decide Whether to Integrate Ordinance with Construction Stormwater & IDDE | 3.2 | 0.1 | 85000 | 8500 |  | 8500
3.e. Develop & Implement Stakeholder Participation Plan | 3.5 | 0.15 | 70000 | 10500 | 5000 | 15500
3.f. Develop Draft Ordinance | Ch. 3, Tool #2 | 0.3 | 70000 | 21000 | 3000 | 24000
3.g. Project Plan Review, Inspection & Maintenance Loads | Ch. 3, 5, 6, 7 | 0.03 | 85000 | 2550 |  | 2550
3.h. Adopt Ordinance Through Public Process | Ch. 3 | 0.2 | 85000 | 17000 | 1000 | 18000
Task 3 Subtotal |  |  |  | 64650 | 11000 | 75650
PHASE 1 SUBTOTAL |  |  |  | 196900 | 51000 | 247900
TOTAL PROGRAM DEVELOPMENT |  |  |  | 450950 | 187000 | 637950
ANNUAL PROGRAM OPERATION |  |  |  | 201300 | 53000 | 254300
* FTEs = Full Time Equivalents
** Annual Cost/FTE was approximated using the following assumptions about program staff: Program Administrator @ $100,000; Stormwater/Watershed Engineer @ $85,000; Engineering Technician/Watershed Planner @ $70,000; GIS/Database Specialist @ $70,000; Stormwater/Engineering Inspector @ $60,000; Clerical @ $55,000. Annual Cost is assumed to include salary and benefits.
*** Costs for actual maintenance tasks varies depending on the responsibilities of the local program versus private responsible parties. See Chapter 7 for a discussion of 3 models for setting up the maintenance program. Expenses in this category can be the highest of any program expense if the local program undertakes active and ongoing maintenance activities involving staff, equipment, materials, vehicles, contractors, etc.

## Phase 2
| Relevant Section or Tool | FTEs (# on annual basis)* | Annual Cost/FTE** | Total Personnel | Other Program Expenses | Total Projected Expenses | Potential Revenue Sources
PHASE 2
4. Develop Stormwater Guidance Manual(s)
4.a. Scope Out Design Guidance Task | 4.3 | 0.02 | 100000 | 2000 |  | 2000 | General Fund, Grants, Utility Fee
4.b. Identify Local, State, or Regional Manual to use as Model or By Reference | Ch. 4, Tool #4 | 0.03 | 70000 | 2100 |  | 2100
4.c. Decide Whether to Integrate Manual with Construction Stormwater (erosion & sediment control manual) | Ch. 4 | 0.1 | 85000 | 8500 |  | 8500
4.d. Develop & Implement Stakeholder Participation Plan | 4.15 | 0.15 | 70000 | 10500 | 5000 | 15500
4.e. Develop Policy & Procedures Manual | 4.4, Tool #4 | 0.25 | 85000 | 21250 | 20000 | 41250
4.f. Develop Technical Design Manual | 4.5 -- 4.13, Tool #4 | 0.75 | 85000 | 63750 | 40000 | 103750
4.g. Adopt the Manuals Through Public Process | Ch. 4 | 0.2 | 85000 | 17000 | 1000 | 18000
4.h. Provide Training on Use of Manuals | 4.14 -- 4.15 | 0.15 | 85000 | 12750 | 5000 | 17750
Task 4 Subtotal |  |  |  | 137850 | 71000 | 208850
5. Create or Enhance Stormwater Plan Review Process
5.a. Scope Out Plan Review Process | 5.3 | 0.02 | 100000 | 2000 |  | 2000 | General Fund, Plan Review Fees, Utility Fee
5.b. Decide Whether to do Review In-House or Contract to Consultant | 5.3 -- 5.5 | 0.02 | 100000 | 2000 |  | 2000
5.c. Create Flowchart or Map Out Review Process | 5.4 | 0.04 | 70000 | 2800 | 1000 | 3800
5.d. Create Forms, Applications, Instruction Materials & Checklists for Applicants & Review Staff | Ch. 5, Tool #5 | 0.06 | 70000 | 4200 | 3000 | 7200
5.e. Forecast Staff Needs & Acquire Staff | 5.3 -- 5.5 | 0.03 | 100000 | 3000 | 3000 | 6000
5.f. Provide Training for Review Staff and Design Consultants | 5.5 -- 5.6 | 0.15 | 85000 | 12750 | 5000 | 17750
5.g. Develop Web-based on Other Tracking System to Track Plans & Approvals | Ch. 8 | 0.15 | 55000 | 8250 | 10000 | 18250
5.h. Set up Peformance Bond Process, Forms, and Tracking System | Tool #6 | 0.2 | 55000 | 11000 | 2000 | 13000
Task 5 Subtotal |  |  |  | 46000 | 24000 | 70000
PHASE 2 SUBTOTAL |  |  |  | 183850 | 95000 | 278850
TOTAL PROGRAM DEVELOPMENT |  |  |  | 450950 | 187000 | 637950
ANNUAL PROGRAM OPERATION |  |  |  | 201300 | 53000 | 254300
* FTEs = Full Time Equivalents
** Annual Cost/FTE was approximated using the following assumptions about program staff: Program Administrator @ $100,000; Stormwater/Watershed Engineer @ $85,000; Engineering Technician/Watershed Planner @ $70,000; GIS/Database Specialist @ $70,000; Stormwater/Engineering Inspector @ $60,000; Clerical @ $55,000. Annual Cost is assumed to include salary and benefits.
*** Costs for actual maintenance tasks varies depending on the responsibilities of the local program versus private responsible parties. See Chapter 7 for a discussion of 3 models for setting up the maintenance program. Expenses in this category can be the highest of any program expense if the local program undertakes active and ongoing maintenance activities involving staff, equipment, materials, vehicles, contractors, etc.

## Phase 3
| Relevant Section or Tool | FTEs (# on annual basis)* | Annual Cost/FTE** | Total Personnel | Other Program Expenses | Total Projected Expenses | Potential Revenue Sources
PHASE 3
6. Inspect Post-Construction BMPs During Construction
6.a. Scope Out Inspection Process | 6.2 | 0.02 | 100000 | 2000 |  | 2000 | General Fund, Inspection Fee, Utility Fee
6.b. Decide Whether to use In-House Inspectors or Contractors | 6.5 | 0.02 | 100000 | 2000 |  | 2000
6.c. Create Checklists, As-Built Certification Forms, and Other Forms Needed for Inspection | 6.4, Tool #5 | 0.05 | 70000 | 3500 | 3000 | 6500
6.d. Forecast Staff Needs & Acquire Inspection Staff or Utilize Existing Staff | Ch. 6 | 0.03 | 100000 | 3000 | 3000 | 6000
6.e. Provide Training for Inspectors & Contractors | 6.5 | 0.15 | 85000 | 12750 | 5000 | 17750
6.f. Develop Web-based or Other Tracking System to Track Inspections & Enforcement Actions | Ch. 8 | 0.15 | 55000 | 8250 | 2000 | 10250
Task 6 Subtotal |  |  |  | 31500 | 13000 | 44500
7. Develop Maintenance Program
7.a. Scope Out Maintenance Program | 7.3 | 0.02 | 100000 | 2000 |  | 2000 | General Fund, Maintenance Inspection Fees, Utility Fee
7.b. Decide on Maintenance Approach & Make Level of Service Policy Decisions | 7.4 | 0.03 | 100000 | 3000 |  | 3000
7.c. Decide Whether to use In-House Inspectors, Contractors, or Rely on Responsible Parties for Maintenance Inspections | Ch. 7 | 0.02 | 100000 | 2000 |  | 2000
7.d. Decide Whether to use In-House Resources, Contractors, or Responsible Parties for Routine & Structural Maintenance Tasks & Repairs | Ch. 7 | 0.02 | 100000 | 2000 |  | 2000
7.e. Create Checklists, Inspection Forms, and Enforcement Tools | 7.4, Tool #5 | 0.05 | 70000 | 3500 | 3000 | 6500
7.f. Forecast Staff and Equipment Needs and Acquire Resources | Ch. 7 | 0.03 | 100000 | 3000 | 3000 | 6000
7.g. Create & Disseminate Outreach Materials for Responsible Parties | 7.4 -- 7.6 | 0.1 | 70000 | 7000 | 15000 | 22000
7.h. Develop Web-based or Other Tracking System to Track Inspections & Enforcement Actions | Ch. 8 | 0.15 | 55000 | 8250 | 2000 | 10250
Task 7 Subtotal |  |  |  | 30750 | 23000 | 53750
8. Track, Evaluate & Monitor Your Program
8.a. Scope Out Evaluation & Monitoring Tasks | Ch. 8 | 0.02 | 100000 | 2000 |  | 2000 | General Fund, Utility Fee
8.b. Decide on Monitoring Protocols | Ch. 8 | 0.04 | 85000 | 3400 |  | 3400
8.c. Develop Tracking & Reporting Tools to Track Key Program Elements | Ch. 8 | 0.03 | 85000 | 2550 | 5000 | 7550
Task 8 Subtotal |  |  |  | 7950 | 5000 | 12950
PHASE 3 SUBTOTAL |  |  |  | 70200 | 41000 | 111200
TOTAL PROGRAM DEVELOPMENT |  |  |  | 450950 | 187000 | 637950
ANNUAL PROGRAM OPERATION |  |  |  | 201300 | 53000 | 254300
* FTEs = Full Time Equivalents
** Annual Cost/FTE was approximated using the following assumptions about program staff: Program Administrator @ $100,000; Stormwater/Watershed Engineer @ $85,000; Engineering Technician/Watershed Planner @ $70,000; GIS/Database Specialist @ $70,000; Stormwater/Engineering Inspector @ $60,000; Clerical @ $55,000. Annual Cost is assumed to include salary and benefits.
*** Costs for actual maintenance tasks varies depending on the responsibilities of the local program versus private responsible parties. See Chapter 7 for a discussion of 3 models for setting up the maintenance program. Expenses in this category can be the highest of any program expense if the local program undertakes active and ongoing maintenance activities involving staff, equipment, materials, vehicles, contractors, etc.

## Program Operation
| Relevant Section or Tool | Annual FTEs (# on annual basis)* | Annual Cost/FTE** | Total Personnel (Annual) | Other Program Expenses (Annual) | Total Projected Expenses (Annual) | Potential Revenue Sources
Program Operation Annual Cost
4. Stormwater Guidance Manual(s)
4.o.1. Update the Manuals At Least Every 5 Years | 4.14 | 0.05 | 85000 | 4250 | 2000 | 6250 | General Fund, Plan Review Fees, Inspection Fee, Maintenance Inspection Fees, Utility Fee
5. Stormwater Plan Review Process
5.o.1. Review Stormwater Plans | Ch. 5, Tool #5 | 1.5 | 85000 | 127500 | 4000 | 131500
6. Inspect Post-Construction BMPs During Construction
6.o.1. Inspect BMPs During Construction | Ch. 8 | 0.25 | 60000 | 15000 | 10000 | 25000
7. Maintenance Program
7.o.1. Inspect BMPs for Maintenance | Ch. 9 | 0.75 | 60000 | 45000 | 20000 | 65000
7.o.2. Conduct Maintenance Tasks*** | Ch. 10 | variable | variable | variable | variable | variable
8. Track, Evaluate & Monitor Your Program
8.o.1. Write Annual Reports for Program Compliance & Other Program Reports & Documents | Ch. 8 | 0.03 | 85000 | 2550 | 2000 | 4550
8.o.2. Maintain the Tracking System | Ch. 8 | 0.1 | 70000 | 7000 | 15000 | 22000
Program Operation Subtotal |  |  |  | 201300 | 53000 | 254300
TOTAL PROGRAM DEVELOPMENT |  |  |  | 450950 | 187000 | 637950
ANNUAL PROGRAM OPERATION |  |  |  | 201300 | 53000 | 254300
* FTEs = Full Time Equivalents
** Annual Cost/FTE was approximated using the following assumptions about program staff: Program Administrator @ $100,000; Stormwater/Watershed Engineer @ $85,000; Engineering Technician/Watershed Planner @ $70,000; GIS/Database Specialist @ $70,000; Stormwater/Engineering Inspector @ $60,000; Clerical @ $55,000. Annual Cost is assumed to include salary and benefits.
*** Costs for actual maintenance tasks varies depending on the responsibilities of the local program versus private responsible parties. See Chapter 7 for a discussion of 3 models for setting up the maintenance program. Expenses in this category can be the highest of any program expense if the local program undertakes active and ongoing maintenance activities involving staff, equipment, materials, vehicles, contractors, etc.

## positions
Stormwater Program Administrator | 100000
Stormwater/Watershed Engineer | 85000
Engineering Technician or Watershed Planner | 70000
Engineering Inspector | 60000
GIS/Database Technician | 70000
Clerical | 55000