## Pond-Wetland
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Stormwater Pond and Wetland Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Type of stormwater pond or wetland (check all that apply)
| a. | Permanent pool sized for full WQv
OR
Shallow wetland sized for full WQv
OR
Micropool
| b. | Extended detention
| c. | Ties into groundwater
| d. | Pond with some wetland plantings
| e. | Multiple pond system
2. | Type of wetland to be created
| a. | Emergent
| b. | Forested
3. | Type of pretreatment facility |  |  |  |  | Pretreatment must be provided
| a. | Sediment forebay
| b. | Grass filter strip
| c. | Other |  |  |  | Type:
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of facility details, landscaping and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
2. | Stormwater runoff diverted around facility or treated with proper erosion and sediment control practices
3. | Tree save and non-compaction areas marked in field
4. | Facility location staked out and cleared
| a. | Embankment/berm location stripped of all vegetation, topsoil and organic matter
5. | Pipe and appurtenances delivered and inspected prior to construction
| a. | Materials
| b. | Diameters
| c. | Dimensions
C. | Excavation/Grading
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Excavation and grading conform to plans
| a. | Embankment/berm core trench excavated and backfilled with suitable material
| b. | Suitable fill material used for construction of embankment/berm
| c. | Compaction completed in accordance with approved plans and specifications
| d. | Embankment/berm elevations, slopes and top widths are correct
| e. | Impounded area excavated/graded according to plans
| f. | Aquatic and safety benches provided in accordance with approved plans
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pretreatment facility installed correctly
| a. | Location, size and depth of facility are correct
2. | Inlet(s) and inlet protection installed according to plans
3. | Liner installed correctly
4. | Riser/outlet structure installed correctly
| a. | Location, dimensions and type of riser are correct |  |  |  | Type of riser:
| b. | Riser located within embankment
| c. | Riser base excavated or formed on stable subgrade
| d. | Riser base set to design elevation
| e. | Riser equipped with removable trash rack
| f. | Location, dimensions and type of low flow orifice are correct
| g. | Low flow orifice installed correctly and adequately protected from clogging
| h. | Pond drain system installed correctly
| i. | Pond drain equipped with adjustable control valve
5. | Outfall pipe (barrel) installed correctly
| a. | Invert at proper elevation and grade
| b. | Waterproof pipe connectors and gaskets properly installed
| c. | Anti-seep collars properly spaced and have watertight connections to pipe
6. | Emergency overflow structure/spillway installed according to plans
7. | Adequate buffer provided
E. | Vegetation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Vegetation complies with approved planting plan and specifications
2. | Embankment/berm and principal spillway kept free of woody vegetation
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Contributing drainage area stabilized
2. | Construction sediment removed from stormwater pond/wetland and pretreatment facility
3. | Pretreatment facility installed and operational
4. | Inlet(s) installed and operational
5. | Configuration, size and depth of stormwater pond/wetland is correct
6. | Vegetation established
7. | Riser/outlet structure installed and operational
8. | Emergency overflow structure/spillway installed and operational
9. | Maintenance access routes provided
10. | Flow diversions removed; runoff reaches facility
G. | Permit Approval and Documentation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Facility constructed within drainage easement
2. | As-built plans submitted and approved
3. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
4. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## Infil-Filt-Bioret
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Infiltration/Filtration/Bioretention Practice Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Type of facility (check all that apply)
| a. | Infiltration
| b. | Filtration
| c. | Bioretention
| d. | Extended detention (storage for Cpv, Qp, Qf)
2. | Facility Location
| a. | Surface
| b. | Underground
3. | Filtration Media
| a. | No filtration media (e.g. dry well)
| b. | Sand
| c. | Bioretention soil
| d. | Peat
| e. | Other
4. | Hydraulic configuration
| a. | On-line facility
| b. | Off-line facility
5. | Type of pretreatment facility |  |  |  |  | Pretreatment must be provided
| a. | Sediment forebay (above ground)
| b. | Sedimentation chamber
| c. | Grass channel
| d. | Grass filter strip
| e. | Plunge pool
| f. | Stone diaphragm
| g. | Other |  |  |  | Type of pretreatment facility:
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of facility details, landscaping and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
| a. | If infiltration practice, facility is not used as sediment basin during construction
2. | Stormwater runoff diverted around facility
3. | Tree save and non-compaction areas marked in field
4. | Facility location staked out and cleared
C. | Excavation/Grading
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Excavation and grading conform to plans
| a. | Location, size and depth of facility are correct
2. | If infiltration practice, underlying soils not compacted during excavation
3. | Soil stockpile located away from facility and stabilized with vegetation and/or silt fence
4. | Embankment/berm constructed according to plan
| a. | Suitable fill material used for construction of embankment/berm
| b. | Compaction completed in accordance with approved plans and specifications
| c. | Embankment/berm elevations, slopes and top widths are correct
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | If off-line facility, flow diversion structure installed according to plans
2. | Pretreatment facility installed according to approved plans
3. | Inlet(s) and inlet protection installed according to plans
4. | Structural components (e.g. foundation, walls) installed according to plans
| a. | Materials tested per local requirements
5. | Liner installed correctly, if applicable
6. | Filter bed composition, depth and installation conforms to approved plans and specifications
7. | Riser/outlet structure installed correctly
| a. | Location, dimensions and type of riser are correct
| b. | Riser equipped with removable trash rack
| c. | Location, dimensions and type of low flow orifice are correct
| d. | Low flow orifice installed correctly and adequately protected from clogging
| e. | If a filtration system, underdrain system installed correctly
8. | Emergency overflow structure/spillway installed according to plans
E. | Vegetation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Vegetation complies with approved planting plan and specifications
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Contributing drainage area stabilized
2. | If off-line facility, flow diversion installed and operational
3. | Pretreatment facility installed and operational
4. | Inlet(s) installed and operational
5. | Configuration, size and depth of bioretention facility conforms with approved plans
6. | Permeability of planting bed verified through in situ soil testing
7. | Vegetation established
8. | Riser/Outlet Structure installed and operational
9. | Emergency overflow structure/spillway installed and operational
10. | Maintenance access routes provided
11. | Flow diversions removed; runoff reaches facility
G. | Permit Approval and Documentation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Facility constructed within drainage easement
2. | As-built plans submitted and approved
3. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
4. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## Open Channel
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Open Channel System Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Type of open channel system
| a. | Dry swale
| b. | Wet swale
| c. | Other |  |  |  | Type of system:
2. | Type of pretreatment facility
| a. | Sediment forebay
| b. | Check dam
| c. | Grass filter strip
| d. | Stone diaphragm
| e. | Other |  |  |  | Type of pretreatment facility:
| f. | None
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of facility details, landscaping and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
2. | Stormwater runoff diverted around facility or treated with proper erosion and sediment control practices
3. | Tree save and non-compaction areas marked in field
4. | Facility location staked out and cleared
C. | Excavation/Grading
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Excavation and grading conform to plans
| a. | Location and dimensions of open channel are correct
2. | Compaction of underlying soils minimized during excavation
3. | Soil stockpile located away from facility and stabilized with vegetation and/or silt fence
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pretreatment facility installed according to approved plans
2. | Inlet(s) and inlet protection installed according to plans
3. | Planting bed composition, depth and installation conforms to approved plans and specifications
4. | Riser/outlet structure installed according to plans
| a. | Location, dimensions and type of riser are correct
| b. | Riser equipped with removable trash rack
| c. | Location, dimensions and type of low flow orifice are correct
| d. | Low flow orifice installed correctly and adequately protected from clogging
| e. | If dry swale, underdrain system installed correctly
E. | Vegetation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Vegetation complies with approved planting plan and specifications
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Contributing drainage area stabilized
2. | Construction sediment removed from open channel system
3. | Pretreatment facility installed and operational
4. | Inlet(s) installed and operational
5. | Configuration and dimensions of open channel system conforms with approved plans
6. | If dry swale, permeability of planting bed verified through in situ soil testing
7. | Vegetation established
8. | Riser/outlet structure installed and operational
9. | Maintenance access routes provided
10. | Flow diversions removed; runoff reaches facility
G. | Permit Approval and Documentation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Facility constructed within drainage easement
2. | As-built plans submitted and approved
3. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
4. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## Natural Area
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Natural Area Conservation & Restoration Credit - Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Type of natural area conservation
| a. | Forest
| b. | Prairie
| c. | Other
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of limit of disturbance, construction fencing requirement, construction signs, and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
2. | Construction fencing and signs erected
3. | Restoration site preparation conducted, if applicable
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Tributary drainage area stabilized
2. | Any construction impacts to the conservation area are repaired (e.g. erosion or sedimentation)
3. | Permanent signage installed
4. | Restoration planting completed & stabilized, if applicable
G. | Permit Approval and Documentation
Y = Yes N = No N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
2. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## Sheetflow
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Sheetflow to Buffer Credit - Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Sheet flow drainage area
| a. | All pervious area
| b. | Includes impervious areas
2. | Buffer protects:
| a. | Stream
| b. | Lake or pond
| c. | Wetland
| d. | Other
3. | Buffer's natural condition
| a. | Forest
| b. | Prairie/grassland
| c. | Other
4. | Buffer meets width requirement |  |  |  |  | Required buffer width:
5. | Reforestation/restoration required?
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of limit of disturbance, construction (temporary) fencing & signage requirement, and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
2. | Construction fencing and signs erected, as per plan
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Buffer width and contributing drainage areas match the dimensions and slopes shown on the plans
2. | The average slope of the contributing area is 5% or less
OR
Level spreader installed correctly
3. | Reforestation/restoration plantings installed according to approved plan
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Tributary drainage area stabilized
2. | Any construction impacts to the buffer area are repaired (e.g. erosion or sedimentation)
3. | Permanent signage installed
4. | Flow diversions are removed; flow is directed to the buffer
5. | Reforestation/restoration completed & stabilized
G. | Permit Approval and Documentation
Y = Yes N = No N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
2. | As-built plans submitted, if applicable
3. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## IC Disconnection
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Impervious Area Disconnection Credit - Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
Key Questions
Item |  |  |  | X |  | Comments
1. | Type of impervious area disconnected
| a. | Rooftop
| b. | Parking
| c. | Other
2. | Compensatory device type (include if pervious area flow path is less than required minimum length); see separate plan review checklist for device
| a. | Dry well
| b. | French drain
| c. | Raingarden
| d. | Other |  |  |  | Other device:
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of limit of disturbance and sequence of construction
| b. | Review of required inspections and certificates
| c. | Ensure coordination with individual builders in cases where rooftop disconnection will be used.
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
2. | Individual builders install silt fence or appropriate ESC controls (rooftop disconnection)
C. | Excavation/Grading
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Excavation and grading conform to plans
2. | Receiving pervious areas not compacted during excavation
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Downspout or impervious surface will drain to receiving pervious area after erosion and sediment controls are removed
2. | Receiving pervious areas and contributing drainage areas match the dimensions and slopes shown on the plans
3. | Level spreader installed according to plan
4. | Compensatory device installed according to plan (if required)
E. | Vegetation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Vegetation complies with approved planting plan and specifications
2. | Topsoil mixture, soil amendments, and soil compaction comply with plan
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Contributing impervious areas are stabilized
2. | For paved areas, wait for 2 storm events after paving to direct runoff to pervious area
3. | Receiving pervious area is stabilized
4. | Flow diversions are removed; flow is directed to the receiving pervious area
G. | Permit Approval and Documentation
Y = Yes N = No N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
2. | As-built plans submitted, if applicable
3. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by:

## Grass Channel
Project Name:
Location:
File Number:
Date of Submittal:
Inspector(s):
Date:
Time:
Grass Channel Credit - Construction Inspection Checklist
Development Status (Active, Inactive, Complete):
Stage of Construction (Pre-Construction, Installation, etc):
A. | Pre-Construction
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Pre-construction meeting
| a. | Review of limit of disturbance and sequence of construction
| b. | Review of required inspections and certificates
B. | Site Preparation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Erosion and sediment controls installed properly and according to approved plans
C. | Excavation/Grading
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Excavation and grading conform to plans
D. | Installation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | After erosion and sediment controls are removed, drainage area to grass channels matches area shown on plans
2. | Grass channels match the dimensions and slopes shown on the plans.
3. | Erosion control blanket or turf reinforcement mat installed properly, if applicable
E. | Vegetation
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Topsoil mixture, soil amendments, and soil compaction complies with plan
2. | Vegetation complies with approved planting plan and specifications
F. | Final Inspection
S = Satisfactory U = Unsatisfactory N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Tributary drainage area stabilized
2. | Grass channel is stabilized
3. | Flow diversions removed; flow is directed to the grass channel
G. | Permit Approval and Documentation
Y = Yes; N = No; N/A = Not Applicable
Item |  |  | S | U | N/A | Comments
1. | Performance bond status
| a. | Not released
| b. | Partial release
| c. | Full release
2. | As-built plans submitted & approved
3. | Certificate of completion issued
Additional Comments:
Actions to be Taken: |  |  |  | X
1. | No action necessary; continue routine inspections
2. | Correct noted deficiencies |  |  |  |  | Correct by:
| a. | 1st notice
| b. | 2nd notice
3. | Submit modifications to project plans |  |  |  |  | Submit by: